| Issue | 1 (draft) |
| --- | --- |
| Document ID | EIS-man-manplan-1d |
| Document File | /tmp/in/input.doc |
| Authors | Matthew Whyndham, MSSL Veronique Gorel, UCL/MSSL |
| Date | December, 1998 |

- Contents

1.	3

Introduction	3

2.	General Management	3

2.1.	Responsibilities of Institutions	3

2.2.	Organisation of Staff	3

2.3.	The System Design Team	3

2.4.	Planning and Reporting	4

2.5.	Archiving of Project Material	6

2.6.	Equipment	6

2.7.	Documentation standards	6

Document Identification System	6

Documents created within EIS	6

Example	7

Documents which originate outside EIS	8

3.	Systems Engineering Management	9

3.1.	General Approach to Systems Engineering	9

3.2.	Model Philosophy	9

Breadboards (BB)	9

Pre-flight models (PM, MTM, TTM)	10

Flight Model (FM) and Spares	11

3.3.	Management of Requirements	11

The User Needs document	12

The System Requirements document	12

The System Specifications document	12

3.4.	Definition of System Design and Interfaces	12

The Design document	12

3.5.	Evaluation of System Performance	13

3.6.	Design Criteria	13

3.7.	Reviews	14

Preliminary design review	14

Critical design review	15

3.8.	Treatment of Risk	15

Programmatic Risk	16

Operational Risk	16

3.9.	AIV	16

3.10.	Product Assurance	17

3.11.	Configuration Management	17

# Introduction

This document is the top level plan for management and systems engineering for Solar-B EIS (the EUV Imaging Spectrometer).

This plan will eventually supersede the management plan in the UK proposal. It also covers the activities of non-UK institutions.

# General Management

## Responsibilities of Institutions

The initial breakdown of responsibilities is indicated in the UK proposal (p 37). The details are subject to changes in the future, depending on design evolution. When finally agreed the breakdown will be listed here.

At the time of writing, the funding parameters for the US partner is not known, although the overall budget for US involvement in Solar-B as a whole is indicated in the NASA AO. In the UK the overall funding profile for each participant has been agreed with PPARC.

## Organisation of Staff

- Figure 1 : EIS organigram.

Figure 1  shows an organigram showing staff roles and reporting lines - mainly within the UK. The main chain of responsibility is from ISAS, through the UK Principal Investigator (PI) to the Project Manager.

All science-related correspondence in the project should be copied to the UK PI, Len Culhane. All technical correspondence should be initiated with, or copied to, the Project Manager (PM).

In order to formulate the scientific and technical requirements of the instrument, the PM will work closely with the PI and will attend meetings of the Science Team.

## The System Design Team

The System Design Team (SDT) will have a central role in forming the design of the instrument in response to the as-stated requirements, and implementation of that design. The SDT meetings will be chaired by the Project Manager and will include the individuals named in the technical disciplines shown in the diagram. For institutes other than MSSL, these represent the points of contact for those institutes. The SDT will seek advice and information from others from time to time.

The SDT will hold regular meeting chaired by the PM. The main purpose of these meetings will be to advance the resolution of technical issues affecting the design and implementation of the system. Other functions are listed (non-exclusively) in Table 1.

| System Design Team functions | Notes |
| --- | --- |
| System design | Identification and resolution of system-level issues |
| SEMP | System Engineering Management Plan, iteration and concurrence |
| WBS | Work Breakdown Structure, development and concurrence |
| Requirements | Development of system functional requirements, system specifications, system test requirements amd any required subsystem documentation |
| Selection of Design Criteria |  |
| Interface Definition | With spacecraft and internal |
| Project Management Activities | Detailed Schedules, costing |
| Testing |  |
| Product Assurance |  |
| Configuration Management |  |
| Reviews |  |

Table 1. Roles of the system design team.

Minutes of SDT meetings will be made available to all project participants.

## Planning and Reporting

In addition to this document, there are other documents which relate to the planned work and actual progress of that plan. These include

- The work breakdown structure

- The schedule

- The budget

- An overview schedule is maintained by the PM and a summary chart issued (~monthly) to:

the system design team (SDT)

all local project managers

the PI

ISAS

- Minutes of meetings:

SDT meetings

MSSL project review meetings

Project Management group meetings

Other institutional project planning meetings (TBD)

Funding agency steering committee meetings

The contents of the schedule are discussed at (and formulated by) the SDT meetings. Meetings of the SDT or relevant subsets are expected ~monthly on average, but no longer than two months apart. Brief minutes of these meetings will be made generally available and circulated to the above. All significant systems engineering decision-making is done by or with the agreement of this group, which has representation from all parties having technical involvement in the instrument.

At MSSL, a Project Review Meeting (PRM) is held on a monthly at which the PM will make a report concerning the general progress of the project, with a particular focus on activities within MSSL. Other institutes may have similar internal mechanisms. The PM will make his PRM reports available in the same way as the SDT meeting minutes.

At (TBD) intervals, there will be a Project Management Group (PMG) meeting, at which the hardware groups are all represented by their local managers. The minutes of these meetings will be available to the funding agencies. It is anticipated that this meeting can be an adjunct to the SDT meetings.

At intervals (2-3 times per year) there will be a meeting of the PPARC EIS steering committee, to which each UK participant project manager will make a report and financial statement and other materials as requested.

There are four major areas of the system engineering activity which will be embodied in their individual plans. These will either be included in this document or presented seperately should their size warrant it. They are as follows

Requirements Management Plan

Configuration Management Plan

Interface Management Plan

Integrated Logistics Support Plan

Numbers in brackets refer to the relevant section in (Systems Engineering Management).

As the work progresses, there will be a large number of design documents and drawings. Each hardware model will have an associated master design document which will describe and identify the elements which are included in that model and provide references to the relevant drawings, documents and code. The manner in which the design evolves with respect to the various design reviews will be stated in the Configuration Management Plan (reference required).

Deviations of the actual hardware from the design condition are detailed in Non-conformance/Failure/Anomaly Reports. The format of these and the procedures for the resolution of the problems they describe will also be described in the Configuration Management Plan.

## Archiving of Project Material

need for archive

show audit trail of development decisions

allow later use within project institutions of generated designs and hardware

formats within the electronic document - permitted, official

use of archive to distribute material

propagation of the archive

maintenance of links within project documents - types of link

documentation standards - templates, required information, requested information

configuration control system

## Equipment

Storage of equipment

## Documentation standards

### Document Identification System

All documents in EIS are uniquely identified by an alphanumeric string. Document Identifiers in the EIS project conform to the following general scheme. As far as possible, all documents are stored electronically, and the storage location in the archive (the file name) can be identified directly with the document identifier.

There is a system for documents generated within EIS and a notation for documents generated outside.

#### Documents created within EIS

- Internal Document identifiers have five fields

| Field | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| Purpose | Project Name | Subsystem | component or lower level system | Label | Issue details |
| Notes | "EIS" is used to distinguish project documents from those in other projects | These are the first level items in the WBS | Lower level items in WBS | This field describes the content of the document. If possible use a unique, memorable string. | Any numeral with optional suffix "d" indicating draft status. A single point may be used to differentiate minor releases. |

Fields 2 and 3 should be taken from the WBS issued by the project manager.

The full document identifier is constructed from these fields, separated by ‘-’ (hyphen). “EIS” is written in capitals and the rest are lower case. It is recommended to show such identifiers in italic to distinguish them from surrounding text.

For example, the following shows the format : EIS-unit1-section2-swnotes-3.27, where Unit 1 and Section 2 are phrases in the WBS. The Label “swnotes” indicates that the document might contain Software Notes. The final numeral indicates that the document is at Issue 3, release 27.

File names are constructed from the same document identifier fields, using whatever separator characters are required by the file system (e.g. ‘/’ or ‘\’). An additional suffix is used to denote the document format (e.g. .txt, .doc, .pdf). The file types which may be encountered is TBD.

The full location is found be prefixing the location of the document archive (this may vary depending on site and implementation).

#### Example

Suppose that Issue 2 of the STM Focal Plane Assembly Requirements list is denoted by

EIS-fpa-stm-reqlist-2

This is the identifier. The corresponding file name depends on the method of delivery of the archive and the format in which the document is stored. The Label will be concatenated with the Issue suffix.

Therefore in the archive stored at \\mssljs\solar-b (on Windows NT - directories separted by ‘\’) it is located at

- \\mssljs\solar-b\EIS\fpa\stm\reqlist2.doc

(The .doc indicates a Word document.)

Suppose the same archive is available through a web server http://eis-www.rummidge.ac.uk/ with the archive rooted at "documents". Then Issue 4 of the same document might be available as a PDF file as

http://eis-www.rummidge.ac.uk/documents/EIS/fpa/stm/reqlist4.pdf

#### Documents which originate outside EIS

External documents are denoted differently. If the document has a clear number or other concise reference (as in a Journal Paper) then that is used. Otherwise If the document does not have a clear number then it is given a serial number in a table of such documents maintained by the project manager. These are of the form

EIS-x-###

The letter x denotes the fact that it is an external document. ### may be any number.  For example:

EIS-x-2 : The Solar-B Mission - Final Report of the Science Definition Team, June 19, 1997. (Various authors). http://wwwssl.msfc.nasa.gov/ssl/pad/solar/sdt-rpt.htm

# Systems Engineering Management

## General Approach to Systems Engineering

In this plan, the term “system” means the EIS instrument.

The systems engineering approach adopted in this project should ensure that there is :

- Thorough understanding of the system requirements.

- Complete knowledge and prediction of the system performance.

- Adequate control of the development of subsystems and systems interfaces 
(to the required performance, on time, under budget).

- Agreement as to the required performance of each subsystem.

Since the resources available to not extend to the employment of full time systems engineer, the responsibility for systems engineering is held collectively by the system design team. Additionally, the management techniques should not be laborious, and therefore the approach to systems engineering is relatively informal in most areas. However, particular attention is paid to documenting the needs, requirements and constraints of the system and subsystems. Refer to "management of requirements" later in this document.

## Model Philosophy

The Model Philosophy describes the intermediate stages of design, development and test, the order and approximate timing of these stages and their relationship to the final, delivered instrument.

The Model philosophy for Solar-B (including EIS) is very similar to that employed in previous missions conducted by the ISAS (the Japanese Agency for space science). Some of the details, such as the names given to certain models, differ somewhat from ESA and NASA practice. In this document we have adopted the Japanese terminology.

The system model philosophy consists of Breadboards (BB), a Prototype Model (PM),  a mechanical and structural model or models, and the Flight Model (FM). All models except the Breadboards are “deliverable” items, that is, they will be integrated with a model or models of the spacecraft and other payload items.

### Breadboards (BB)

- for technological development at subsystem level.

- Breadboard models of many subsystems will be developed, of the purpose of which will be to demonstrate the suitability of technology to be employed in later models, to expose any unforeseen problems which  may exist and to further refine the system requirements.

- The areas to be addressed within the UK are : focal plane assembly, electronics box, door. There is likely to be a need for a software development platform.

- Subsystem level tests (exact content of these tests is TBD) will be performed on these partial breadboards.

- US: Optic breadboard.

### Pre-flight models (PM, MTM, TTM)

- for development and testing at system level.

- A Prototype Model is used to verify the functional operation of the system, including its interfaces with the spacecraft and ground segment. Another model (or two models) is used for further spacecraft level interface design verification.

- Prototype Model (PM) : This will not be fully functional in that it will not contain optical elements. Mechanical and thermal properties need not be representative of the final design, except where necessary for validation in the areas which are tested. The validation tests to be performed on this model will include (TBD) :

- System level (EIS) electrical performance

- initial system (EIS) level electromagnetic compatibility

- electrical interfaces with spacecraft

- instrument software

- interaction with spacecraft and ground segment software

- The PM will also be used as a platform for further electronic and software development.

- There will be two models of the spacecraft which will be used for mechanical and thermal tests. They are called the Mechanical Test Model (MTM) and the Thermal Test Model (TTM). These will undergo separate programs of tests. Consequently there is a need for a suitable model of EIS to participate in each of these tests. It is unclear whether this requirement can be satisfied with a single Structural-Thermal Model (STM) or whether two separate models will be required. For purpose of this discussion assume that two such models will exist.

- Mechanical test Model (MTM): this is highly representative in mechanical terms but will contain no optics or electronics. All the mechanical qualification tests will be done on this model :

- vibration and acoustic tests

- confirmation of subsystems vibrations level

- mechanical qualification of various subsystems

- Thermal Test Model (TTM): This will have sufficient representation to allow thermal qualification of the design. It will contain no optics or electronics. The following tests are done on this model:

- thermal balance

- thermal vacuum

- The results of both the MTM and TTM tests could be used in the further development of the instrument flight model (although the schedule does not allow significant interval between MTM/TTM test and FM manufacture).

- Comment : There are no optical components in any of the preflight models. Some additional methods of gaining confidence in the optical technology (production, alignment, etc.) may be necessary.

### Flight Model (FM) and Spares

- For calibration, launch and operation.

At this stage of development a high level of confidence in the design should have been obtained from previous models.

The flight model (FM) is the only model to be fully calibrated. It is also the only model that contains a set of optical elements (not including optics breadboards).

It will be used for system level mechanical and thermal testing together with performance verification/ validation tests to demonstrate full compliance with requirements. The level of the testing is TBD (e.g. environmental tests could be at a lower - “acceptance” - level than the qualification tests carried out during the MTM/TTM phase).

Some further, hopefully minor, development of the FM design can be expected during FM integration.

There will not be a complete spare instrument, nor indeed a complete set of spare parts, but rather a spares philosophy will be adopted which involves the provision of key items and contingency planning. This posture is adopted as a means of reducing costs. Critical items which require spares will be identified prior to FM parts procurement.

## Management of Requirements

The development of the system (the EIS instrument) is controlled at the highest level by three documents, namely the User Needs document, the System Requirements document and the System Specifications document. Refer to Figure 2.

- Figure 2 : Structure of the top level documentation tree

The User Needs document (ref) expresses the goals which the system’s operation will achieve.

The System Requirements document (ref) is partly a Functional Requirements Document. It reflects a subset of the needs by stating the functional requirements of the system in measurable terms (what the system must do and how well it must do it). Any additional requirements or technical and managerial constraints are also contained in this document. This covers the spacecraft resource allocation, interfaces and environmental characteristics.

The System Specification document (ref) describes how the system will meet the requirements. This will refer to the technology to be employed (whereas the Requirements do not). It is recognised however that there will be some iteration between the capabilities of the solution and these requirements, the aim being to arrive at an achievable set of requirements.

Each of these documents is described in more detail below.

If there are competing solutions, which otherwise meet the requirements, then each will have its own Specifications document. Each Specification document will refer for further detail to a Design Document. The Design document refers to all other technical documentation related to that solution, including where appropriate a set of Requirements, Specifications and a Design for each subsystem.

Competing solutions will be subject to evaluation based on the Design Critera.

### The User Needs document

There is a wide interest in the outcome of the Solar-B mission in the solar physics communities of the U.K., Japan and the U.S.A. The interests of these communities are partly represented by the funding agencies in each countries. Their interests have also been expressed in reports such as Solar-B Science Definition Team - Final Report, and others.

However, this document records the wishes of the EIS consortium, as represented by the Principal Investigator (PI) and the Science Team.

For the purposes of the User Needs document the PI and the Science Team are regarded as the Users of EIS.

### The System Requirements document

This document contains the system requirements which emanate from the user needs, called scientific requirements, and the other requirements. The later are technical constraints (due to accommodation of the instrument on the spacecraft), managerial constraints, interface requirements, and others (TBD).

### The System Specifications document

## Definition of System Design and Interfaces

### The Design document

- subsystem details

- relating system and subsys requirements

- and perfomance back again

- interfaces generally

- system level interface view

- say something how interfaces will develop

## Evaluation of System Performance

## Design Criteria

Design Criteria constitute the rules for prioritising competing designs. Competing designs are those which meet the requirements (and are therefore satisfactory in other respects). Very often these choices are made implicitly. Here we explicitly state each Criterion that is presently known, firstly in general areas applicable to the whole system and secondly in particular technology areas or subsystems.

This list is presented as material for discussion in the SDT.

The general criteria are as follows:

- Management = the triangle

- Performance. It would be advantageous to exceed the performance levels indicated in some of the requirements. These include at least Temporal Resolution, Spatial Resolution, Spectral Resolution and Sensitivity.

- Cost. Budgets are fixed. No or little advantage in spending less than the budget. Penalties for exceeding agreed budget (including the effort of budget renegotiation, even if possible).

- Management risk (Schedule). Date of schedule driver (the launch) is fixed. Therefore a strong incentive to ensure timely delivery of system.

- Technology

- Innovation	A compromise has to be reached between the use of existing skills and the development of new technologies. A “good” design should contain both. Can certain technologies be identified as being favoured for development? Can we say what the innovation “rate” should be?

- modularity : 	allow sharing of the work. e.g. with other institutes. Also related to testing.

- Interfaces 	(if they are simple, systems are more complex, if they are complex the modularity is more difficult to achieve). Human cost of interfaces.

- Ease of Integration/Testability

- Lifetime / Reliability

- Commercial Value. May be some opportunities for commercialisation of technology. Not a high priority.

- others ...

- Areas where Tradeoff can be expected

- Spectrometer Configuration : Gregorian, Cassegrain

- Wavelength Range !

- Camera styles : Analog output vs. digital output

- Structural Material : Aluminium vs. composite

- Data compression : location in EIS or outside (MDP).

- Processor type

- software development system / language

- others ...

## Reviews

This section will contain details of all the reviews. The following are scheduled at the time of writing:

- Preliminary design review

- Critical design review

- Other reviews may be required during the programme. These may include the following:

- System requirements reviews

- Flight model critical design review

- Flight to readiness review

### Preliminary design review

- The purpose at the preliminary design review is to demonstrate the feasibility of the design. The follfol will be submitted for review in:

- All specification documents, including software specifications

- System hierarchy

- Interface description (i.e. documentation of each subsystem interface)

- Test plans

- Logistic support plants

- The management plan itself and associated reference documents

- Following this review detailed design can begin. The interfaces are frozen (under configuration control?).

- Details (internals) of the subsystems need not be fixed at this time. There could be major areas requiring further study.

### Critical design review

- The purpose of the critical design review is to gain confidence in the detailed design so that production (of EM and STM level subsystems) can begin. The risks of implementation should be well understood and acceptable.

- Material to be available at this review will include (as well as updated versions of the documents brought before the PDR):

- Schematics

- Interface and drawings

- Drawings of major components

- Data flow diagrams

- Results of feasibility studies and tradeoff analyses

## Treatment of Risk

This section will supercede the risk analysis in the UK proposal.

Attitudes

Areas of Concern

Method of response

Most types of risk fall into following broad categories:

Programmatic risk: the probability of not delivering a working (i.e. to the required specification) instrument because of a human or organisational failure

Operational risk: the failure probability of the instrument during its operation

### Programmatic Risk

Some sources of programmatic risk:

confusion caused by project documentation, including this

misunderstanding of interfaces

failure of contractors to deliver component to required performance or cost

change of launch date

failure, at late stage, during environmental testing

incompatiblity with spacecraft discovered during integration

### Operational Risk

failure modes analysis required?

some sources:

meteoroid ingress

contamination of optics or detector

loss of optics motion

door failure

spacecraft misalignment – thermal effects

radiation damage, e.g. to detector, memory, processor

on board software error

bad command

loss of functionality in electronics

loss of attitude information

## AIV

= Assembly, Integration, Verification

includes (or refers) model test matrix

includes regimes for calibration

## Product Assurance

cleanliness - see Plan

testing - see AIV

parts, processes and materials selection

## Configuration Management

models & design freezes

ncr/ecr

document archive (again)

This is the  “build it - test it -fix it” paradigm.

In some systems engineering texts, the term “Systems Engineering Process Paradigm” is used to denote this concept.